# Regional strategies for implementing the fourth phase of the global monitoring plan

The fourth phase of the global monitoring plan (GMP-4) involves distinct strategies tailored to each region by their respective regional organization groups (ROGs). These strategies are designed to coordinate the collection and management of data on persistent organic pollutants (POPs) within the regions. Each ROG has selected global coordination group (GCG) members to oversee implementation, communicate with national authorities, and organize activities for compiling and reporting data. The ROGs have outlined specific tasks for each member, including country communication, coordination activities, report preparation, and areas where financial support or technical assistance from the Secretariat is needed.

## Africa

### Members:

#### ROG Members:

Martin Benoit Ngassoum (Cameroon), Vincent Madadi (Kenya), Taelo Letsela (Lesotho), Halimatou Koné Esp Traore (Mali), Otmani Anas (Morocco), Bondi Gevao (Sierra Leone)

#### GCG Members:

Vincent Madadi (Kenya) (Regional Coordinator), Martin Benoit Ngassoum (Cameroon), Otmani Anas (Morocco)

### Regional coordination and communication

The ROG members agreed to adopt a coordination model similar to that of previous phases, with minimal adjustments to accommodate new members. Each ROG member will oversee communication with Stockholm Convention (SC) focal points and national contacts in their respective subregions. The six subregions established in phase one will continue to be used in phase four. Each subregion is led by a designated ROG member responsible for maintaining contact with SC focal points and national contacts.

These ROG members will gather data on air, water, and maternal milk from various national programmes and agencies within their subregions, working closely with the United Nations Environment Programme/Global Environment Facility’s Global Chemicals Monitoring Programme (UNEP/GEF GCMP) project team and the Stockholm Convention Regional Centres (SCRC) located in Algeria, Kenya, Senegal, and South Africa and the Basel Convention Coordinating Centre (BCCC) in Nigeria.

Additionally, the ROG members agreed to prioritize electronic communication during phase four, ensuring that all communications with countries are copied to SC focal points and national contacts. They also request that the Secretariat provide an updated list of all SC focal points and national contacts in the region.

Table 1 below summarizes the agreed subregional divisions and their respective ROG members.

Table 1: Division of responsibilities among African ROG members.

| African ROG members | Regional Centres | Countries assigned to ROG members |
| --- | --- | --- |
| Martin B. Ngassoum (Cameroon) | SCRC-Senegal BCCC-Nigeria | Cameroon Chad Togo Democratic Republic of Congo Central Africa Republic Gabon Equatorial Guinea Congo |
| Vincent Madadi (Kenya) | SCRC-Kenya | Burundi Comoros Eritrea Kenya Madagascar Rwanda Seychelles Uganda Ethiopia |
| Taelo Letsela (Lesotho) | SCRC-South Africa | Botswana Eswatini Lesotho Malawi Mauritius Mozambique Namibia South Africa Zambia Zimbabwe |
| Halimatou Koné Esp Traore (Mali) | SCRC-Senegal | Burkina Faso Cabo Verde Côte d’Ivoire Guinea Guinea-Bissau Mali Niger Senegal Benin |
| Otmani Anas (Morocco) | SCRC-Algeria | Algeria Egypt Libya Mauritania Morocco Tunisia Sudan South Sudan Djibouti |
| Bondi Gevao (Sierra Leone) | SCRC-Senegal | Angola São Tomé and Príncipe Sierra Leone Liberia Gambia Nigeria Ghana Ethiopia Somalia Tanzania |

### Data collection sources

The ROG coordinator will oversee the collection of comparable POPs monitoring data by ROG members through SC focal points, national operational contacts, and UNEP/GEF GCMP project focal points. Once gathered, the ROG coordinator will circulate the data among ROG members, UNEP, and the Secretariat for review to ensure it meets GMP standards before it is entered into the GMP data warehouse using the standardized data template.

Data from existing monitoring programmes will also be centralized with the ROG coordinator, reviewed by GCG members, and uploaded to the GMP data warehouse. Once stored, the data will be available for review, approval, and download for inclusion in the regional report.

### Drafting, consultation and report preparation timeline

A drafting team or consultant, working closely with the UNEP/GEF GCMP project team, will be selected by June 2025, with contractual arrangements managed by the coordinating institution. This drafting team will compile the first draft of the regional report by December 2025. The ROG members will then review and finalize the draft at a dedicated workshop, aiming for regional adoption by September 2026. The workplan outlining the steps and timeline for this effort is detailed in Table 2.

Table 2: Workplan for the African ROG.

| Activity | Timing |
| --- | --- |
| Drafting team setup | January–June 2025 |
| Data collection | June–December 2025 |
| Initial draft completion | February 2026 |
| Drafting workshop | March–August 2026 |
| Regional review | September 2026 |
| Final editing, translation (English and French) and publication | October–November 2026 |

### Capacity gaps and support needed from the Secretariat

The following key areas of support are essential to facilitate the effective implementation of the regional monitoring plan and related activities:

- Financial support for consultants, report editing, publishing, and translation;

- Financial support for the drafting workshop;

- Updated contact information for SC focal points and assistance with introductions between ROG members and national authorities;

- Liaison with the UNEP/GEF GCMP project team.

## Asia and the Pacific

### Members:

#### ROG Members:

#### Minghui Zheng (China), Ved Prakash Mishra (India), Yoshikatsu Takazawa (Japan), Hasanthie Sandarekha Dissānayake (Sri Lanka), Chalongkwan Tangbanluekal (Thailand), Anass Ali Saeed Al-Nedhary (Yemen)

#### GCG Members:

Minghui Zheng (China) (Regional Coordinator), Yoshikatsu Takazawa (Japan), Hasanthie Sandarekha Dissānayake (Sri Lanka)

### Regional coordination and communication

The members of the ROG for the Asia-Pacific region are responsible for coordinating data collection and capacity-building activities within their respective subregions. They will also support the development of the fourth regional monitoring report by collaborating with countries to address specific data needs and gaps. Table 3 summarizes the sub-regional framework of responsibilities assigned to each ROG member, highlighting the countries they oversee and their role in maintaining contact with SC focal points and national contacts.

ROG members will gather data on air, water, and maternal milk from various national programmes and agencies within their subregions. They will work closely with the UNEP/GEF Global Chemicals Monitoring Programme (GCMP) project team and the Stockholm Convention Regional Centres (SCRCs) located in China, India, Indonesia, Kuwait, and the Secretariat of the Pacific Regional Environment Programme (SPREP) in Samoa.

The Eastern European (EE) ROG will oversee the following countries: Kazakhstan, Kyrgyzstan, Tajikistan, Turkmenistan, and Uzbekistan.

The Western Europe and Other Groups (WEOG) ROG will oversee Cyprus.

Table 3: Division of responsibilities among Asia-Pacific ROG members.

| Asia-Pacific ROG members | Regional Centres | Countries assigned to ROG members |
| --- | --- | --- |
| Minghui Zheng (China) | SCRC-China | Brunei Darussalam China Democratic People’s Republic of Iran (Islamic Republic of) Mongolia Pakistan Republic of Korea |
| Ved Prakash Mishra (India) | SCRC-India | Afghanistan Bangladesh Bhutan India Maldives Nepal |
| Yoshikatsu Takazawa (Japan) | SCRC-Indonesia | Cambodia Indonesia Japan Lao People’s Democratic Republic Myanmar Philippines Republic of Korea Singapore Viet Nam |
| Anass Ali Saeed Al-Nedhary (Yemen) | SCRC-Kuwait | Bahrain Iraq Jordan Kuwait Lebanon Oman Qatar Saudi Arabia State of Palestine Syrian Arab Republic United Arab Emirates Yemen |
| Hasanthie Sandarekha Dissānayake (Sri Lanka) | SPREP | Cook Islands Fiji Kiribati Marshall Islands Micronesia (Federated States of) Nauru Niue Sri Lanka |
| Chalongkwan Tangbanluekal (Thailand) | SPREP | Palau Papua New Guinea Samoa Solom Islands Thailand Tonga Tuvalu Vanuatu |

### Data collection sources

Data sources in this region include:

- East Asian POPs Monitoring Network: Monitoring air quality across various countries in East Asia;

- UNEP/GEF Project on POPs Monitoring in East Asia Region and UNEP/GEF GCMP Project: Monitoring air, water, and maternal milk;

- UNEP/GEF Project on POPs Monitoring in the Pacific Islands Region and UNEP/GEF GCMP: Data from air, water, and maternal milk from Pacific Island countries;

- National POPs Monitoring Programs: Programs in China, Japan, Republic of Korea, et al.;

- United Nations University (UNU)/Shimadzu perfluorooctane sulfonic acid (PFOS) Monitoring Project: Focuses on water quality.

### Drafting, consultation and report preparation timeline

The initial drafting team will be supported by the Government of Japan, working in close collaboration with the UNEP/GEF GCMP project team. The workplan outlining the steps and timeline for this effort is detailed in Table 4. The report will be finalized with their assistance.

Table 4: Workplan for the Asia-Pacific ROG.

| Activity | Timing |
| --- | --- |
| Drafting team setup | January–June 2025 |
| Data collection | June–December 2025 |
| Initial draft completion | February 2026 |
| Drafting workshop | March–August 2026 |
| Regional review | September 2026 |
| Final editing and publication | October–November 2026 |

### Capacity gaps and support needed from the Secretariat

Financial support from the Secretariat is needed for the consultant and the drafting workshop. Technical support from the Secretariat is also required to liaise with the UNEP/GEF GCMP project team and the GMP data warehouse.

## Eastern Europe

### Members:

#### ROG Members:

#### Anahit Aleksandryan (Armenia), Kateřina Šebková (Czech Republic), Marina Stefova (North Macedonia), Anna Cumanova (Republic of Moldova), Zarema Amirova (Russian Federation), Ivan Djurickovic (Serbia)

#### GCG Members:

Kateřina Šebková (Czech Republic) (Regional Coordinator), Marina Stefova (North Macedonia), Anna Cumanova (Republic of Moldova)

### Regional coordination and communication

The Czech Republic will lead the Eastern European (EE) ROG, with support from the Stockholm Convention Regional Centre hosted by RECETOX, Masaryk University, Czech Republic. The team will ensure consistent communication and coordination with countries in the region, focusing on updating monitoring programmes, evaluating laboratory capabilities, and managing data in the GMP data warehouse. The specific division of responsibilities among EE ROG members is outlined in Table 5.

The 23 EE countries in the region are as follows: Albania, Armenia, Azerbaijan, Belarus, Bosnia and Herzegovina, Bulgaria, Croatia, Czech Republic, Estonia, Georgia, Hungary, Latvia, Lithuania, Montenegro, North Macedonia, Poland, Republic of Moldova, Romania, Russian Federation, Serbia, Slovakia, Slovenia, and Ukraine.

Additionally, based on an agreement with the Asia-Pacific region, the EE ROG will oversee POPs monitoring in the following 5 countries: Kazakhstan, Kyrgyzstan, Tajikistan, Turkmenistan, and Uzbekistan.

The division of work will be based on topics rather than splitting countries among different ROG members. The current topics and responsibilities are as follows:

- Analyze information from country questionnaires:

  - Collect and analyze responses about country activities and programmes, including updates to existing POPs monitoring programmes and new activities in core media;

  - Engage SC focal points via letters and questionnaires (all ROG members to contribute);

- Verify laboratory capacity:

  - Assess the capacity of POPs laboratories in the region through a specific questionnaire;

  - Identify challenges faced by regional laboratories and support participation in intercalibration studies;

- Identify and analyze research data and projects:

  - Work on identifying research data, projects, and published articles related to POPs monitoring in core and non-core media for the period 2020–2024/2025, with the aim of identifying trends;

- Collaborate with other conventions.

  - Engage with other conventions and initiatives that may have relevant data on POPs.

Table 5: Division of responsibilities among EE ROG members.

| EE ROG members | Responsibilities |
| --- | --- |
| Anahit Aleksandryan (Armenia) | Analysis of information from questionnaires from Caucasian countries, including the Asia-Pacific ones. |
| Kateřina Šebková (Czech Republic) | Overall coordination and communication with SC focal points in the region and leader of the drafting team. |
| Marina Stefova (North Macedonia) | Analysis of information from questionnaires about laboratories and research data on POPs in the scientific literature published in the region from 2020 to 2025. |
| Anna Cumanova (Republic of Moldova) | Analysis of information from questionnaires, as well as information and data on POPs from other conventions (namely CLRTAP and EMEP). |
| Zarema Amirova (Russian Federation) | Collection of information and handling of data specific to the Russian Federation and Belarus, including new data from the period 2020–2025. |
| Ivan Djurickovic (Serbia) | Identification of information from databases, national regulatory systems, and questionnaires on national programmes related to POPs monitoring in core and non-core media. |

### Data collection sources

The ROG will prioritize monitoring data for POPs in air, human tissues, and water, specifically for PFOS. Additional data will be collected from other relevant sources if they meet the established criteria for quality and traceability. The ROG has agreed to include all data from previous reports that comply with quality standards and to incorporate new data from 2020 onwards. The collection will focus on all relevant POPs, including newly identified ones, with a preference for core media (air, human tissues, and water for PFOS). Data from other media should only be included for the most relevant POPs, prioritizing newly listed POPs.

Media-specific data collection:

- Air data:

  - Data will be sourced from established networks, including the Monitoring Network Programme (MONET), Global Atmosphere Passive Sampling (GAPS) Network, and the European Monitoring and Evaluation Programme (EMEP)/EBAS database;

  - Supplementary information will be included from relevant national activities, such as verifying European Environment Agency (EEA) databases and EMEP work, including the Task Force on Modeling;

- Human tissues data:

  - Data will be considered from the Human Biomonitoring Partnership initiative (HBM4EU) activities, national milk surveys, and Partnership for the Assessment of Risks from Chemicals (PARC);

  - Published information on human biomonitoring will also be included;

- Water data:

  - Data will be sourced from the EU Water Framework Directive reports, OSPAR, other conventions relevant to the region, project data, and national regulatory data;

  - Information from the European Environment Agency will be incorporated as well;

- Other matrices/complementary information:

  - Data for other media (e.g., soil and water for additional POPs) will focus on pesticides and levels reported through national regulatory systems;

  - Preference will be given to data sets with the potential to track time trends, where sampling procedures and data analyses are known and traceable.

Data submission and reporting:

- Data submission will follow the format used in the GMP data warehouse, using standardized reporting templates;

- Data should be submitted to the GMP data warehouse as soon as they are ready;

- A letter from the EE ROG will be sent to SC focal points to request new information and collect updates;

- The region will utilize data outputs from the GMP data warehouse (e.g., maps, charts, tables) to illustrate trends, data availability, baselines, and summary information for each matrix;

- The final report will be prepared in English only.

### Drafting, consultation and report preparation timeline

Table 6 provides a workplan for the EE ROG, outlining key activities and respective timelines.

Table 6: Workplan for the EE ROG.

| Activity | Timing |
| --- | --- |
| Drafting team setup | January–June 2025 (ROG members + RECETOX experts) |
| Data collection | June–December 2025 (could be extended until May/June 2026) |
| Initial draft completion | June 2026 |
| Drafting workshop | August–September 2026 |
| Regional review | September–October 2026 (online, in consultation with countries in the region) |
| Final editing and publication | October–December 2026 |

### Capacity gaps and support needed from the Secretariat

The region requires support from the Secretariat for consultants and a drafting workshop to finalize the report. Specifically, the EE region seeks assistance for consultants to work on chapters addressing water, human matrices, and long-range transport, as well as to provide data analysis and interpretation for the EE region. Additionally, one face-to-face drafting meeting of the ROG and consultants is proposed to take place in Brno, Czech Republic, during the mid to late second half of 2026, to finalize the regional report.

Drafting team and roles:

A drafting team at RECETOX will lead the report preparation, with contributions from the following experts:

- Branislav Vrana: Expertise in water-related chapters;

- Klára Komprdová and Pavel Čupr: Focus on human matrices;

- Jiri Kalina: Specialization in air-related chapters.

Proposed support from the Stockholm Convention Regional Centre at RECETOX:

The following support is required from the Regional Centre to ensure the report's timely and thorough preparation:

- Data compilation: Consolidate all EE data into a database by May 2026, allowing ROG sufficient time to review it;

- Data analysis and interpretation: Assist with analyses and interpretation of data across all core matrices, utilizing data analysts;

- Water chapter drafting: Draft the chapter on POPs in EE waters, incorporating information from the Water Framework Directive, Aqua Gaps Programme, and other relevant sources;

- Human matrices chapter drafting: Draft the chapter on POPs in human matrices in the EE region;

- Modeling for long-range environmental transport (LRET): Use the expertise of Autonomic noncommercial organization (ANO) Vostok/ Meteorological Synthesizing Centre “East” (MSCE) (Alexey Gusev) for modeling LRET in the region.

## Latin America and the Caribbean

### Members:

#### ROG Members:

#### Karina Miglioranza (Argentina), Sandra De Souza Hacon (Brazil), Ricardo Barra (Chile), Trecia David Garnath (Guyana), Arturo Gavilan Garcia/Tania Ramírez (Mexico), Alejandra Torre (Uruguay)

#### GCG Members:

Sandra De Souza Hacon (Brazil), Ricardo Barra (Chile), Alejandra Torre (Uruguay) (Regional Coordinator)

### Regional coordination and communication

The Latin America and the Caribbean (GRULAC) ROG members will continue the approach used for the second and third reports, coordinating with SC focal points to gather country-specific POPs data.

To communicate with countries each ROG member has the responsibility to address several countries according to Table 7.

Table 7: Division of responsibilities among GRULAC ROG members.

| GRULAC ROG members | Countries assigned to ROG members |
| --- | --- |
| Karina Miglioranza (Argentina) | Argentina Bolivia Colombia Panama Peru |
| Sandra De Souza Hacon (Brazil) | Antigua and Barbuda Brazil Suriname Trinidad and Tobago Venezuela |
| Ricardo Barra (Chile) | Belize Chile El Salvador Guatemala Honduras Nicaragua |
| Trecia David Garnath (Guyana) | Guyana Dominica Saint Kitts and Nevis Saint Lucia Saint Vincent & the Grenadines. |
| Arturo Gavilán/Tania Ramírez (Mexico) | Bahamas Barbados Dominican Republic Haiti Jamaica Mexico |
| Alejandra Torre (Uruguay) | Costa Rica Cuba Ecuador Paraguay Uruguay |

The planned activities and timeline for the GRULAC ROG are outlined in Table 8.

Table 8: Activities and timeline for GRULAC ROG.

| Activity | Details | Timing |
| --- | --- | --- |
| Communication with SC focal points | The Secretariat sends a letter to all SC focal points, introducing the ROG members and facilitating contact with the SC focal points for information exchange. The letter should also request information about additional technical contact points (national contacts). | January 2025 |
| Online meeting with SC focal points and national contacts | Organize an online meeting to introduce the project and explain the need for national support. | February 2025 |
| Information request to SC focal points | Request information from each SC focal point on core media and other media for POPs. | March 2025 |
| Mapping analytical capabilities | Assess the analytical capabilities for POPs within the region, particularly for new POPs. | March 2025 |
| Identification of POP sources and matrices | Identify potential POP sources and other relevant matrices in the region. | March 2025 |
| Compilation of monitoring recommendations | Develop recommendations for monitoring POPs in the region in preparation for COP-12 in 2025. | March 2025 |
| Collaboration with regional and global activities | ROG members will engage with other regional and global activities to gather monitoring data. | January–June 2025 |
| Review of open literature | ROG members will review information available in open literature for each country. | June–December 2025 |
| Dissemination of ROG and GMP activities | Promote ROG and GMP activities within the region through outreach and communication. | January–December 2025 |

### Data collection sources

Key sources include global, regional, and national monitoring programmes, and the ROG will request data submission from focal points to support the GMP’s effectiveness evaluation.

The relevant countries in the region are as follows:

- North America: Mexico;

- Central America: Belize, Costa Rica, El Salvador, Guatemala, Honduras, Nicaragua, Panama;

- South America: Argentina, Bolivia (Plurinational State of), Brazil, Chile, Colombia, Ecuador, Guyana, Paraguay, Peru, Suriname, Uruguay, Venezuela (Bolivarian Republic of);

- Caribbean: Antigua and Barbuda, Bahamas, Barbados, Cuba, Dominica, Dominican Republic, Grenada, Haiti, Jamaica, Saint Kitts and Nevis, Saint Lucia, Saint Vincent and the Grenadines, Trinidad and Tobago.

### Drafting, consultation and report preparation timeline

A drafting team comprising ROG members, a consultant, a translator, and an editor will oversee the report's preparation, with a teleconference and in-person meeting scheduled to finalize the draft. The workplan for this effort is outlined in Table 9.

Table 9: Workplan for the GRULAC ROG.

| Activity | Timing |
| --- | --- |
| Drafting team setup | January–June 2025 |
| Data collection | June–December 2025 |
| Initial draft completion | February 2026 |
| Drafting workshop | March–August 2026 |
| Regional review | September 2026 |
| Final editing and publication | October–November 2026 |

### Capacity gaps and support needed from the Secretariat

Financial support from the Secretariat is required for the consultant, meetings, translation, and publication.

## Western Europe and Other Group

### Members:

#### ROG Members:

#### Tom Harner (Canada), Gerhard Lammel (Germany), Knut Breivik (Norway), Linda Linderholm (Sweden)

#### GCG Members:

Tom Harner (Canada) (Regional Coordinator), Linda Linderholm (Sweden)

### Regional coordination and monitoring

The WEOG region will use the latest available data from ongoing national, regional, and global monitoring programmes, including those reported during previous GMP phases, as well as new programmes and special projects. This will also include peer-reviewed papers reporting spatial and temporal trend information on POPs, with a focus on core media. The drafting process will be managed through regular virtual meetings, with the first meeting planned for December 2024. Executive summaries from monitoring programmes will serve as the basis for the report.

In the Arctic context, the WEOG GMP4 report will incorporate new information from the Arctic Monitoring and Assessment Programme (AMAP) on a Temporal Trends Assessment up to 2024, which includes the effects of climate change. This assessment will be available in April 2026. Additionally, AMAP will provide a Local Sources Assessment of POPs monitoring.

Precipitation data for per- and poly-fluoroalkyl substances (PFASs) will continue to be used to address gaps in air monitoring data, alongside ice core data, which will be reported for the first time in GMP4.

In addition, new developments relevant to the GMP will be considered, such as non-targeted analytical methods, transformation products of POPs, emerging chemicals, and linkages between POPs monitoring and studies related to health, biodiversity, and climate change.

Finally, other sources of information on emissions will be explored. This will include primary emissions based on chemical release inventories as well as secondary emissions in relation to effectiveness of control measures, which may be particularly relevant for POPs with limited monitoring data.

### Drafting and consultation and report preparation timeline

Assigned experts will lead data analysis for each media type, aiming to complete the draft report by June 2026 and finalize it by November 2026. The timeline and activities for this process are outlined in Table 10.

Table 10: Workplan for the WEOG ROG.

| Activity | Timing |
| --- | --- |
| Drafting team setup | January–June 2025 |
| Data collection | June–December 2025 |
| Initial draft completion | February 2026 |
| Drafting (ongoing) | March–August 2026 |
| Regional review | September 2026 |
| Final editing and publication | October–November 2026 |

South Sudan is neither a Party nor a Signatory to the Stockholm Convention.

Turkmenistan is neither a Party nor a Signatory to the Stockholm Convention.

Turkmenistan is neither a Party nor a Signatory to the Stockholm Convention.

https://ebas.nilu.no/.

https://www.eu-parc.eu/.

Haiti is a Signatory but not a Party to the Stockholm Convention.

Haiti is a Signatory but not a Party to the Stockholm Convention.

Two more members of the regional organization group from the WEOG region need to be identified.